## Slide 1: Powerflex vs non-HCI
Comparison of Work Required

## Slide 2: “Work expands to fill the time available for its completion.”
Parkinson’s law

## Slide 3: Project Timeline
Chart: 484 days from 26 April 2021 – 31 AUGust 2022
Design | 114
Engineering | 162
DC Build | 88
^
30 Sep 2021
^
2 May2022
* As of 13 May 2021

## Slide 4: Work Resource
Chart: 5824 Man-days With headcount of 16
Design | 1824
Engineering | 2592
DC Build | 1408
* With headcount of 16 in Q2 2021
Notes: Need to roughly calculate the effort required for each team in EC (in man-days), then add together for this chart. I made non-HCI a total of all possible effort, then took 20% off for HCI in Design and Build.

## Slide 5: Can Powerflex reduce work required?
Dell’s HCI solution

## Slide 6: PowerFlex Strengths
All Flash storage – extremely high performance
Async block level replication
Firmware management
  Version compliance reporting
  Upgrade automation
  Certification and packaging
VMware Hypervisor
  Provisioning
  Lifecycle management
Flexible block storage provisioning

## Slide 7: Extra Benefits
Automated deployment of vanilla RHEL and Windows on BM
Cloudlink provides integrated key management
VLAN setup automation for ToR switches*
Management and performance dashboards
Storage volume provisioning via API, CLI, and dashboard
* Not currently in consideration

## Slide 8: 295 days saved
147 days during project + 148 days in annual operations

## Slide 9: Work reduction detail
KEY POINT Choosing Powerflex now saves at least 2 months of research into alternate products. This allows us to begin into the next step - lab testing the Linux build - sooner.
 | Engineering | Operations
Decision-making | 40 days. Product research avoided | --
Dashboards | 40 days. Product research avoided | --
Linux bootstraping | -- | 5 days. ~2 hours/machine *20
VM provisioning (DC build) | -- | 62 days. ~1 hour/machine * 500
Firmware updates | 8 days/yr. 2 days testing & packaging for each quarterly update | 16 days/yr. ~10 minutes/machine done manually for 200 machines (quarterly)
VM lifecycle management | -- | 124 days/yr. ~1 hour/machine * 500, twice annually

## Slide 10: 3% project effort saved
Chart: 
| Powerflex savings
Column1 | 147 | 5677

## Slide 11: Comparison
Chart: Work EFFORT Savings Not considering Parkinson’s law
| Powerflex | Non-HCI
Design | 1744 | 1824
Engineer | 2587 | 2532
DC Build | 1346 | 1408
5824
5677